## Gantt Chart
|  | Bakery Online Ordering |  | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Maya | Leo | Priya | R: Responsible S: Support
|  |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Activity | Task | Time Est. | Progress | 13.4 | 14.4 | 15.4 | 16.4 | 17.4 | 18.4 | 19.4 | 20.4 | 21.4 | 22.4 | 23.4 | 24.4 | 25.4 | 26.4 | 27.4 | 28.4 | 29.4 | 30.4 | 1.5 | 2.5 | 3.5 | 4.5 | 5.5 | 6.5 | 7.5 | 8.5 | 9.5 | 10.5 | 11.5 | 12.5 | 13.5 | 14.5 | 15.5 | 16.5 | 17.5 | 18.5 | 19.5 | 20.5 | 21.5 | 22.5 | 23.5 | 24.5
Discovery | Stakeholder interviews | 2 | 100 | [42 empty] | S |  | R | bar: Week 16 Mon to Week 16 Tue
| Requirements & menu data | 3 | 100 | [43 empty] | R | S | bar: Week 16 Tue to Week 16 Thu
Design | Wireframes | 4 | 100 | [42 empty] | R | S | bar: Week 16 Thu to Week 17 Tue
| Visual design | 6 | 50 | [42 empty] | R |  | S | bar: Week 17 Tue to Week 18 Tue
| Design sign-off | [44 empty] | R | bar: Week 18 Wed
Build | Ordering & checkout | 10 | 0 | [42 empty] | S | R | bar: Week 17 Sat to Week 19 Sun
| Payments integration | 7 | 0 | [43 empty] | R | bar: Week 18 Sat to Week 20 Tue
| Content & photos | 6 | 0 | [42 empty] | S |  | R | bar: Week 18 Wed to Week 19 Wed
Testing | User testing in two shops | 3 | 0 | [42 empty] | R |  | S | bar: Week 20 Wed to Week 20 Sun
| Bug fixes | 4 | 0 | [43 empty] | R | bar: Week 20 Thu to Week 21 Tue
Launch | Launch campaign | 5 | 0 | [42 empty] | S |  | R | bar: Week 19 Sat to Week 21 Fri
| Go live | [45 empty] | R | S | bar: Week 21 Fri
Total
Earned hours | Time estimate × progress, summed
Remaining hours | Total time estimate − earned